## Task4_StakeholderEngagement
Stakeholder | Power | Interest | Strategy | Communication Method | Frequency
Executive Sponsor (CEO) | High | High | Manage closely – involve in key decisions, provide strategic updates, and secure approvals. | Executive briefings, formal reports | Monthly (plus milestone updates)
Program Manager | High | High | Lead actively – coordinate all stakeholders, monitor risks, and ensure alignment with business goals. | Project meetings, dashboards | Weekly
IT/AI Lead | Medium | High | Engage closely – provide technical input, oversee integration, and resolve issues quickly. | Technical workshops, Slack/Teams updates | Twice weekly
Customer Service Manager | Medium | High | Keep involved – ensure adoption, training, and smooth transition for agents. | Training sessions, feedback surveys | Bi-weekly
Marketing Manager | Low | High | Keep informed – align chatbot promotion with brand strategy and customer campaigns. | Email updates, marketing sync calls | Monthly
Data Protection Officer | High | Medium | Keep satisfied – ensure compliance, review data handling, and approve privacy safeguards. | Compliance reports, review meetings | Quarterly
End Customers | Low | High | Monitor and engage – gather feedback, improve usability, and ensure satisfaction. | In-app surveys, email follow-ups | Continuous (post-interaction)