## Risk Matrix Threats
Project: Outdoor Recreation Inc. (ORI) - Majic Mountain CSR
P | 5 | [5 empty] | Top Risks
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1 | Steep trail, altitude challenges, lack of safety prep | Employee injury during hike | Medical emergencies, delays, reputational damage | Provide safety briefing, first aid kits, assign trained staff, ensure waivers signed
B | [6 empty] | R2 | Estimates based on assumptions, unexpected costs | Budget overrun | Exceeding allocated funds, sponsor dissatisfaction | Track expenses closely, set aside contingency fund
A | 3 |  |  | R4 R5 | R2 | R1 | R3 | Poor planning or execution | Reputational damage | Negative community perception, reduced trust | Ensure strong planning, clear communication, and visible leadership presence
B | [6 empty] | R4 | Lack of defined roles and coordination | Volunteer inefficiency | Reduced productivity, incomplete clean-up | Assign clear roles, provide task checklists, appoint team leads
I | 2 |  |  |  |  | R3 | R5 | Catering miscalculation or delivery issues | Food/beverage shortages | Dissatisfied participants, reputational harm | Confirm quantities by confirming numbers of participants and have backup supplies
L
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25

## Risk Matrix Opp
Project:
P | 5 |  |  |  |  | R1 | Top Opportunities
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1 | Poor planning | Negative community perception | Loss of trust and credibility. | Strong planning, clear communication
B | [6 empty] | R2 | Overwork or unsafe conditions | Employee dissatisfaction | Reduced morale and retention | Recognition, balanced workload
A | 3 | [5 empty] | R3 | Inadequate preparation | Customer complaints | Reputational and financial loss. | Ensure stock, train staff
B | [6 empty] | R4 | Subpar delivery | Strained relationships | Reduced future collaboration opportunities. | Deliver quality service, maintain professionalism
I | 2 | [5 empty] | R5 | Event failure | Loss of future CSR initiatives | Missed strategic positioning. | Document lessons, improve planning
L | [6 empty] | R6
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25