## Risk Register Template
Project: Outdoor Recreation Inc. (ORI) - Majic Mountain CSR Date: 28/09/2026
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
R1 | Steep trail, altitude challenges, lack of safety prep | Employee injury during hike | Medical emergencies, delays, reputational damage | Program Manager | Safety | 3 | 5 | 15 | Reports of fatigue, unsafe trail conditions | Provide safety briefing, first aid kits, assign trained staff, ensure waivers signed
R2 | Estimates based on assumptions, unexpected costs | Budget overrun | Exceeding allocated funds, sponsor dissatisfaction | Finance Officer | Logistics | 3 | 4 | 12 | Rising costs, unplanned purchases | Track expenses closely, set aside contingency fund
R3 | Poor planning or execution | Reputational damage | Negative community perception, reduced trust | Program Manager | Financial | 2 | 5 | 10 | Negative feedback, poor media coverage | Ensure strong planning, clear communication, and visible leadership presence
R4 | Lack of defined roles and coordination | Volunteer inefficiency | Reduced productivity, incomplete clean-up | Project Team Leads | Operational | 3 | 3 | 9 | Confusion, duplicated tasks | Assign clear roles, provide task checklists, appoint team leads
R5 | Catering miscalculation or delivery issues | Food/beverage shortages | Dissatisfied participants, reputational harm | Logistics Co-ordinator | Environmental | 3 | 3 | 9 | Higher attendance, catering delays | Confirm quantities by confirming numbers of participants and have backup supplies
R6 | Overwork or unsafe conditions | Employee disengagement | Reduced morale, absenteeism, poor teamwork | HR Manager | Logistics | 3 | 3 | 9 | Complaints, disengagement | Have a recognition plan for the participants, balanced workload
R7 | Inadequate preparation of sales tent | Failed marketing exposure | Customer frustration, reputational harm | Program Manager | Logistics | 2 | 4 | 8 | Stock shortages, poor service | Use data to foreacst sales numbers and apply contigency numbers to the forecasted data
R8 | Subpar delivery of community service | Weak partnerships | Strained relationships, reduced collaboration | CEO / Program Manager | Strategic | 2 | 4 | 8 | Complaints from Magic Mountain/community | Ensure strong planning, clear communication, and visible leadership presence
R9 | Event mismanagement | Loss of future CSR initiatives | Missed strategic positioning | CEO / Program Manager | Strategic | 2 | 4 | 8 | Negative lessons learned, reluctance to repeat | Deliver quality service, maintain professionalism by ensuring proper planning, and risk analysis
Total Risk Score | [7 empty] | 88
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low