## SWOT Worksheet
SWOT Worksheet
Strengths (Cause) | Opportunities (Event)
Strong CEO support and funding commitment ensures resources are available. | Enhanced brand reputation through visible community service
Clear community engagement objective aligns with company values | Improved employee engagement and team bonding, especially for new hires.
Inclusion of new hires fosters team collaboration and cohesion | Marketing exposure via sales tent could generate additional revenue
Established logistics plan (charter buses, box lunches, supplies) demonstrates preparedness. | Strengthened partnerships with Magic Mountain and local community.
Authorization from Magic Mountain to set up tents provides legitimacy and visibility. | Potential for repeat events, establishing ORI as a socially responsible leader.
Weaknesses (Cause) | Threats (Event)
Limited project scope definition and interim risk analysis only (no formal charter yet). | Safety risks during the hike (injuries, fatigue, altitude challenges).
Dependence on employees only (no family participation) may reduce inclusivity. | Budget overruns if unexpected costs arise (e.g., supplies, medical emergencies).
Potential lack of medical or safety preparedness for hiking activity | Poor coordination could lead to low productivity or missed objectives.
Reliance on volunteers without clear role assignments could cause inefficiency. | Employee dissatisfaction if logistics fail (transport delays, inadequate food).
Short timeline and one-day event may limit impact and increase pressure. | Reputational risk if event is poorly executed or perceived as disorganized.