## SWOT Worksheet
SWOT Worksheet
Strengths (Cause) | Opportunities (Event)
Strong CEO support and funding commitment ensures resources are available. | Enhanced brand reputation through visible community service
Clear community engagement objective aligns with company values | Improved employee engagement and team bonding, especially for new hires.
Inclusion of new hires fosters team collaboration and cohesion | Marketing exposure via sales tent could generate additional revenue
Established logistics plan (charter buses, box lunches, supplies) demonstrates preparedness. | Strengthened partnerships with Magic Mountain and local community.
Authorization from Magic Mountain to set up tents provides legitimacy and visibility. | Potential for repeat events, establishing ORI as a socially responsible leader.
Weaknesses (Cause) | Threats (Event)
Limited project scope definition and interim risk analysis only (no formal charter yet). | Safety risks during the hike (injuries, fatigue, altitude challenges).
Dependence on employees only (no family participation) may reduce inclusivity. | Budget overruns if unexpected costs arise (e.g., supplies, medical emergencies).
Potential lack of medical or safety preparedness for hiking activity | Poor coordination could lead to low productivity or missed objectives.
Reliance on volunteers without clear role assignments could cause inefficiency. | Employee dissatisfaction if logistics fail (transport delays, inadequate food).
Short timeline and one-day event may limit impact and increase pressure. | Reputational risk if event is poorly executed or perceived as disorganized.

## Risk Register Template
Project: Date:
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
R1 | Steep trail, altitude challenges, lack of safety prep | Employee injury during hike | Medical emergencies, delays, reputational damage | Program Manager | Safety | 3 | 5 | 15 | Reports of fatigue, unsafe trail conditions | Provide safety briefing, first aid kits, assign trained staff, ensure waivers signed
R2 | Estimates based on assumptions, unexpected costs | Budget overrun | Exceeding allocated funds, sponsor dissatisfaction | Finance Officer | Logistics | 3 | 4 | 12 | Rising costs, unplanned purchases | Track expenses closely, set aside contingency fund
R3 | Poor planning or execution | Reputational damage | Negative community perception, reduced trust | Program Manager | Financial | 2 | 5 | 10 | Negative feedback, poor media coverage | Ensure strong planning, clear communication, and visible leadership presence
R4 | Lack of defined roles and coordination | Volunteer inefficiency | Reduced productivity, incomplete clean-up | Project Team Leads | Operational | 3 | 3 | 9 | Confusion, duplicated tasks | Assign clear roles, provide task checklists, appoint team leads
R5 | Catering miscalculation or delivery issues | Food/beverage shortages | Dissatisfied participants, reputational harm | Logistics Co-ordinator | Environmental | 3 | 3 | 9 | Higher attendance, catering delays | Confirm quantities by confirming numbers of participants and have backup supplies
R6 | Overwork or unsafe conditions | Employee disengagement | Reduced morale, absenteeism, poor teamwork | HR Manager | Logistics | 3 | 3 | 9 | Complaints, disengagement | Have a recognition plan for the participants, balanced workload
R7 | Inadequate preparation of sales tent | Failed marketing exposure | Customer frustration, reputational harm | Program Manager | Logistics | 2 | 4 | 8 | Stock shortages, poor service | Use data to foreacst sales numbers and apply contigency numbers to the forecasted data
R8 | Subpar delivery of community service | Weak partnerships | Strained relationships, reduced collaboration | CEO / Program Manager | Strategic | 2 | 4 | 8 | Complaints from Magic Mountain/community | Ensure strong planning, clear communication, and visible leadership presence
R9 | Event mismanagement | Loss of future CSR initiatives | Missed strategic positioning | CEO / Program Manager | Strategic | 2 | 4 | 8 | Negative lessons learned, reluctance to repeat | Deliver quality service, maintain professionalism by ensuring proper planning, and risk analysis
Total Risk Score | [7 empty] | 88
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low

## Risk Matrix Threats
Project: Outdoor Recreation Inc. (ORI) - Majic Mountain CSR
P | 5 | [5 empty] | Top Risks
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1 | Steep trail, altitude challenges, lack of safety prep | Employee injury during hike | Medical emergencies, delays, reputational damage | Provide safety briefing, first aid kits, assign trained staff, ensure waivers signed
B | [6 empty] | R2 | Estimates based on assumptions, unexpected costs | Budget overrun | Exceeding allocated funds, sponsor dissatisfaction | Track expenses closely, set aside contingency fund
A | 3 |  |  | R4 R5 | R2 | R1 | R3 | Poor planning or execution | Reputational damage | Negative community perception, reduced trust | Ensure strong planning, clear communication, and visible leadership presence
B | [6 empty] | R4 | Lack of defined roles and coordination | Volunteer inefficiency | Reduced productivity, incomplete clean-up | Assign clear roles, provide task checklists, appoint team leads
I | 2 |  |  |  |  | R3 | R5 | Catering miscalculation or delivery issues | Food/beverage shortages | Dissatisfied participants, reputational harm | Confirm quantities by confirming numbers of participants and have backup supplies
L
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25

## Risk Matrix Opp
Project:
P | 5 |  |  |  |  | R1 | Top Opportunities
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1
B | [6 empty] | R2
A | 3 | [5 empty] | R3
B | [6 empty] | R4
I | 2 | [5 empty] | R5
L | [6 empty] | R6
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25