## Roadmap
Project Goal: Launch a new company website to increase online presence and improve customer engagement.
Milestone | Outcomes | Success Metric: | Timeframe | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Market Research and Planning | Understand user needs and define website requirements. | Completion of user surveys and market analysis report. | January - February | bar: Jan to Feb
2. Design Phase | Create a user-friendly and visually appealing website design. | Approval of wireframes and design mockups. | February - March | bar: Feb to Mar
3. Development Phase | Develop the website with all required features and functionalities. | Completion of website development and internal testing. | March-April | bar: Mar to Apr
4. Content Creation | Develop and integrate high-quality content for the website. | Approval of all website content. | March - April | bar: Mar to Apr
5. Testing and Quality Assurance | Ensure the website is bug-free and performs well. | Successful completion of beta testing with no critical issues. | April - May | bar: Apr to May
6. Launch and Marketing | Successfully launch the website and drive initial traffic. | Achieve 10,000 unique visitors in the first month. | May- June | bar: May to Jun

## Gantt chart
[7 empty] | J A N U A R Y | [30 empty] | F E B R U A R Y | [27 empty] | M A R C H | [30 empty] | A P R I L | [29 empty] | M A Y | [30 empty] | J U N E
Ref | Milestones/Tasks | Start Date | End Date | Duration (days) | Team | Dependencies | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Market Research and Planning |  |  |  |  | Milestone
| Conduct user surveys | 2026-01-02 | 2026-01-14 | 13 | bar: J A N U A R Y 2 to J A N U A R Y 14
| Analyse user feedback | 2026-01-15 | 2026-01-22 | 7 |  | Conduct user surveys | bar: J A N U A R Y 15 to J A N U A R Y 22
| Compile list of requirements | 2026-01-23 | 2026-01-26 | 4 |  | Analyse user feedback | bar: J A N U A R Y 23 to J A N U A R Y 26
2 | Design Phase |  |  |  |  | Milestone
| Create wireframe | 2026-01-29 | 2026-02-11 | 14 |  | Compile list of requirements | bar: J A N U A R Y 29 to F E B R U A R Y 11
| Get feedback | 2026-02-12 | 2026-02-14 | 3 |  | Create wireframe | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| Revise wireframe from feedback | 2026-02-15 | 2026-02-18 | 4 |  | Get feedback | bar: F E B R U A R Y 15 to F E B R U A R Y 18
| Develop design mockups | 2026-02-19 | 2026-03-04 | 14 |  | Revise wireframe from feedback | bar: F E B R U A R Y 19 to M A R C H 4
| Approve final designs. | 2026-03-05 | 2026-03-08 | 4 |  | Develop design mockups | bar: M A R C H 5 to M A R C H 8
3 | Development Phase |  |  |  |  | Milestone
| Set up a development environment | 2026-03-09 | 2026-03-10 | 2 | bar: M A R C H 9 to M A R C H 10
| Front-end development | 2026-03-11 | 2026-04-01 | 22 |  | Set up a development environment | bar: M A R C H 11 to A P R I L 1
| Back-end development |  |  | 21 |  | Set up a development environment
| Internal testing |  |  | 10 |  | Front-end development and Back-end development
4 | Content Creation |  |  |  |  | Milestone
| Develop content plan |  |  | 21
| Get feedback on content |  |  | 7 |  | Develop content plan
| Approve content and implement on website |  |  | 8 |  | Get feedback on content
5 | Testing and Quality Assurance |  |  |  |  | Milestone
| Create test cases |  |  | 2
| coduct testing |  |  | 7 |  | Internal testing
| Fix identified issues |  |  | 7 |  | coduct testing
| Final Testing and approval |  |  | 5 |  | Final Testing and approval
6 | Launch and Marketing |  |  |  |  | Milestone
| Define Launch Objectives |  |  | 2
| Develop Marketing Strategy |  |  | 2 |  | Define Launch Objectives
| Develop content for launch and Marketing |  |  | 2 |  | Develop lauch and objectives and Develop Marketing Strategy
| Product campain execution |  |  | 1 |  | Develop content for launch and Marketing
| Product Launch Execution |  |  | 1 |  | Product campain execution
| Evaluate process |  |  | 30 |  | Product Launch Execution