## Template
High-Level Budget: Resource Breakdown Structure Project Name: Develop Real-Time Marketing Intelligence Application for AHI Date: April 2026
WBS identifier # | Work package | Internal personal required | External personnel required | Venue costs | Materials required | Supplies required | Equipment required | Comments | Total direct costs
1.1 | Design Phase | 0 | 90000 | 0 | 0 | 0 | 0 | 50% of App Development Cost | 90000
1.2 | Development Phase | 0 | 0 | 0 | 5000 | 0 | 15000 | Data Feeds and IT Hardware/Software | 20000
1.3 | Testing Phase | 0 | 0 | 0 | 0 | 0 | 35000 | IT Storage and Security Upgrades | 35000
1.4 | Launch & Improvement Phase | 0 | 90000 | 0 | 0 | 0 | 0 | Remaining App Development Cost | 90000
TOTAL cOSTS |  | 0 | 180000 | 0 | 5000 | 0 | 50000 | 0 | 235000
Contingency requirements (10%) | [8 empty] | 23500
Personnel cost requirements | [5 empty] | Note: Update cost categories to reflect actual project requirements
Rate | Name | Hours | Costs
0
0
0
0
0
0
0
0
TOTAL |  |  | 0