Overview:

The Project Charter is the first document created in the Initiation phase. It answers the “what,” “why,” and “who” of the project. The project sponsor must approve the project charter before formal planning can begin.

The Project Charter is often developed based on information provided in a business case, Statement of Work (SOW), or agreement such as a contract, Memorandum of Understanding (MOU), Service Level Agreement (SLA), and so on.

Use this template to create your Project Charter.

Section I: General Project Charter Information

| Charter Item | Comments |
| --- | --- |
| Project name | Develop Real-Time Marketing Intelligence Application for AHI |
| Project goal | Develop an application to provide marketing data in real-time. The app will help AHI gather information and data to better understand the target market and develop strategies in real-time. The project supports AHI's strategic objective of increasing market share and capturing a greater portion of the projected global industry growth of 4.5%–7.5% over the next three years. |
| Project value proposition and benefits | - Enable faster introduction of new and updated products to the target market - Improve the overall AHI customer experience - Enable better positioning to be worked out through analysis of individual product sales - Enable better business decisions - Accelerate the testing of new product concepts - Gain insights into current shoppers and demographics - Enable improved brand tracking |
| Problem or opportunity statement | Currently AHI tracks data using a variety of unlinked systems and depends on manual consolidation efforts. Collecting and analyzing data takes time, delaying decision making. Need to leverage AHI to achieve a higher share of projected global industry growth of 4.5% to 7.5% over the next three years. AHI requires a centralized, automated solution to: - Gather and analyze market intelligence in real time. - Monitor customer preferences and buying behaviors. - Track competitor activities and market share changes. - Reduce manual data collection and reporting efforts. - Accelerate strategic marketing and product decisions. |
| Project schedule | Project kick-off Apr 2026 - Design (May 2026) - Finalize app requirements, analysis, and design - Finalize all IT infrastructure upgrade requirements - Develop (Jun-Aug 2026) - Develop an initial app prototype - Develop the required IT interface - Test App (Sep 2026) - Perform initial beta test - Gather feedback - Upgrade app and IT infrastructure - Launch App (Oct 2026) - Add two new hires to support IT - Train personnel on the new app - Launch the app - Gather feedback - Improve (Nov 2026) - Incorporate feedback - Make adjustments - Monitor app effectiveness - Plan for Version 2 |
| Project manager | Cary Manning - Marketing |
| Approval authority/sponsor | Mary Smithers - Marketing |

Section II: Additional Clarifying Information

| Assumptions or constraints | Constraints: - $250,000 fixed budget. - Strict milestone adherence required : Schedule critical the project must start in April 2026 and the App launched in Nov 2026 - Resource availability: May affect development and testing timelines - Data integration complexity: Potential implementation challenges Assumptions: - IT team will be able to develop a viable app to meet marketing needs. - IT can support the app. - The app will improve marketing effectiveness. 20% ROI in Year 1. - A viable application can be developed within the approved budget. - Users will adopt the application. - The application will improve marketing effectiveness. - Existing IT infrastructure can support the new solution with planned upgrades |
| --- | --- |
| Proposed solution(s) high-level overview | The initial app will perform the following functions: - Identify, understand, and address current and developing segments and target markets (External) - Facilitate easier customer access to AHI products and pricing (External) - Enable secure invoicing and order processing (External) - Track current market trends in the skin care industry in real-time (Internal) - Monitor customer interest and preferences for AHI products based on opinion analysis (Internal) - Generate competitive analysis data by analyzing global sales data (Internal) - Calculate AHI market share and trends by product category (Internal) - Identify competitor products with the largest market share (Internal) |
| Project priorities | 1. Schedule: Cannot deviate from the Nov 2026 deadline. 2. Budget: $250,000 is the goal. 3. Scope: The project supports AHI's strategic objective of increasing market share and capturing a greater portion of the projected global industry growth of 4.5%–7.5% over the next three years. |
| Return on Investment (ROI) | Budget: $250,000 fixed Benefits: - Increased revenue - Increased customer satisfaction - Cost avoidance - Improved product time to market - Improved marketing focus |
| Risks (Potential) | - If the project goes over-budget: reduced ROI - Design flaws will lead to app launch delays - Development delays will lead to app launch delays - IT capability issues can impact on ROI and lead to app launch delays - Internal app development capacity can lead to app launch delays - Data integration issues – current data analysis requires different system |
| Resources required | - IT team: - App Developers - Database admin - Networking Admin - System admin - Additional 2 IT staff - Stakeholders: - Marketing team - Finance team - Project Owner - Data: - Sales data - Competitor data - Customer data - Marketing data - IT hardware - IT storage - Budget |