## Design
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Start
1.1.4.Develop initial design
8 days
1.1.3.Finalize vendor contract
4 days
1.1.1. Define key app functionality requirements
6 days
1.1.2.Identify vendor to design and develop app
5 days
1.1.5.Solicit initial design feedback
2 days
1.1.6.Update design based on feedback
3 days
1.1.7.Gain final design approval
2 days
End
3 days

## Development
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Start
1.2.4.Perform prototype beta test
10 days
1.2.3.Develop an initial prototype
30 days
1.2.1. Implement IT upgrades
15 days
1.2.2.Develop app launch plan
20 days
1.2.5.Solicit beta test feedback
5 days
1.2.6.Update prototype based on feedback
8 days
1.2.7.Gain prototype approval
2 days
End
15 days

## Testing
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Start
1.3.4.Train Marketing Personnel on the New App
5 days
1.3.3.Approve the Launch Plan
3 days
1.3.1.Test the Final App Prototype
8 days
1.3.2.Gain Customer Acceptance
4 days
1.3.5.Begin IT Hiring
10 days
1.3.6.Begin Full-Scale Development
8 days
End
Float
5 days

## Launch and Approve App
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start
Start
End
End
Buffer
Buffer
Start
1.4.4.Finalize new hires
10 days
1.4.3.Document App Issues
10 days
1.4.1.Launch New App
1 day
1.4.2.Monitor App Performance
15 days
1.4.6.Implement app upgrades
12 days
1.4.5.Plan app upgrades
8 days
End
Float
5 days
1.4.7.Plan V2 Upgrades
5 days
1.4.8.Launch App V2
1 day
1.4.9.Complete the final project report
5 days
Float
5 days