## Stacey Analysis Examples
Stacey Diagram Analysis Tool
Project Name | A: Level of Agreement | B: Technology Complexity | Project Score (A x B) | Decision | Comments | Score | Decision
Widget Product Development | 5 | 4 | 20 | Iterative/Agile | Almost no agreement Likely a few knowns, but many unknowns | 21 - 25 | Delay Project
New Server Development | 1 | 2 | 2 | Predictive/Incremental | Requirements are set Known technology, but a few challenges | 8- 20 | Iterative/Agile
Accounts Receivable Process Update | 2 | 2 | 4 | Predictive/Incremental | Generally agreed upon delivery schedule A few changes anticipated. Generally known technology | 1 - 7 | Predictive/Incremental
New Marketing Technology | 3 | 5 | 15 | Iterative/Agile | Moderate agreement rate at 50% High degree of innovation needed to roll out the technology and campaign
Note 1: Agreement scoring normally is an indicator of how much change you can anticipate. The less agreement you have, the more change can be anticipated. Note 2: Agreement scores and complexity can impact the delivery cycles. In most cases, low agreement and high complexity levels normally lead to the need to deliver more frequently to ensure you are meeting project objectives.
Agreement Scoring Criteria | Almost 100% | About 80% | About 50% | Some Agreement 30% | Almost No Agreement
Level of Agreement | 1 | 2 | 3 | 4 | 5
Certainty Scoring Criteria | Known Technology | Known Technology - A Few Challenges | May Require Some Explanation and Prototyping | A Few Knowns--Many Unknowns | Almost 100% New or Unknown Technology
Technology/Innovation | 1 | 2 | 3 | 4 | 5

## Stacey Analysis Blank
Stacey Diagram Analysis Tool
Project Name | A: Level of Agreement | B: Technology Complexity | Project Score (A x B) | Decision | Comments | Score | Decision
App Developmnet | 3 | 4 | 12 | Scrum | Product Owner/Dev Team | 21 - 25 | Delay Project
App Security upgrades | 2 | 4 | 8 | Scrum | Product Owner/Dev Team | 8- 20 | Iterative/Agile
IT Security upgrades | 2 | 2.5 | 5 | Predictive | Product Manager Lead | 1 - 7 | Predictive/Incremental
App training | 2 | 2 | 4 | Predictive | Product Manager Lead
IT storage upgrades | 2 | 2 | 4 | Predictive | Product Manager Lead
IT hardware and software installations | 2 | 1 | 2 | Predictive | Product Manager Lead
IT personell acquisition | 1 | 1 | 1 | Predictive | Product Manager Lead
Note 1: Agreement scoring normally is an indicator of how much change you can anticipate. The less agreement you have, the more change can be anticipated. Note 2: Agreement scores and complexity can impact the delivery cycles. In most cases, low agreement and high complexity levels normally lead to the need to deliver more frequently to ensure you are meeting project objectives.
Agreement Scoring Criteria | Almost 100% | About 80% | About 50% | Some Agreement 30% | Almost No Agreement
Level of Agreement | 1 | 2 | 3 | 4 | 5
Certainty Scoring Criteria | Known Technology | Known Technology - A Few Challenges | May Require Some Explanation and Prototyping | A Few Knowns--Many Unknowns | Almost 100% New or Unknown Technology
Technology/Innovation | 1 | 2 | 3 | 4 | 5