## WBS Template
|  | New Hire Orientation Program |  | Level 1 Project Level
1.1 Project Planning | 1.2 Project Executing |  | 1.3 Project Closure | Level 2 Phase Level
1.1.1 Develop Project Charter | 1.2.1 Orientation Program Design & Content Development |  | 1.3.1 Collect Feedback from New hires and existing employees | Level 3 Work Package Level
1.1.2 Get Project Charter Sign-off | 1.2.2 Develop Orientation Materials & Welcome Packages |  | 1.3.2 Evaluate Program Effectiveness
1.1.3 Identify Stakeholders | 1.2.3 Logistics Coordination |  | 1.3.3 Financial Reconciliation & Cost Reporting
1.1.4 Develop Stakeholder Register | 1.2.4 Employee Equipment & Supply Preparation |  | 1.3.4. Run Lessons Learned workshop
1.1.5 Develop WBS | 1.2.5 Conduct Orientation Day 1 |  | 1.3.5. Update Project Documentation
1.1.6 Develop Project Schedule | 1.2.6 Conduct Orientation Day 2 |  | 1.3.6 Transition Program to HR Operations
1.1.7 Develop budget and cost estimates |  |  | 1.3.7 Project Closure Approval
1.1.8 Develop Communications Plan
1.1.9 Reserve Conference Room
1.2.5 Conduct Orientation Day 1: | 1.2.6 Conduct Orientation Day 2:
1.2.5.1. Breakfast | 1.2.6.1.Breakfast |  |  | Level 4 Work Package Level
1.2.5.2. Conduct Campus tour | 1.2.6.2.New Hires Receive Technical Support
1.2.5.3. Present Innovations inc benefits | 1.2.6.3.New Hires Receive Corporate Badges and Supplies
1.2.5.4. Lunch
1.2.5.3. Unpack Your Perks
1.2.5.4. Conduct Q&A Sessions
1.2.5.4.Presentation on continuing education opportunities.