Instructions: Fill in the fields of this project charter with the information provided in the lab scenario. Click into the column and begin typing to enter information.

| Charter Item | Comments |
| --- | --- |
| Project Name | Develop New Hire Orientation Program |
| Project Goal | Design, develop, and implement a comprehensive New Hire Orientation Program that improves employee onboarding, increases engagement, enhances organizational support, and reduces early employee attrition by preparing and executing the inaugural orientation event on June 1-2. |
| Project Value Proposition and Benefits | The program will: - Improve the new employee experience - Increase employee retention - Strengthen corporate culture - Improve engagement with company benefits and resources - Reduce recruitment replacement costs. Innovations Inc. currently spends approximately $6,000 to recruit each new employee, reducing turnover during the first 45 days can generate significant cost savings. |
| Problem or Opportunity Statement | Innovations Inc. has experienced increasing employee attrition. HR analysis indicates approximately 4% of employees leave within their first week of employment and 20% leave within 45 days. Exit surveys identify ineffective orientation and lack of corporate support as primary causes. The project creates an opportunity to improve retention of current employees and new hires through a structured onboarding program. |
| Project Schedule | Project Start: February 15 Planning & Development: February 15 to May 31 Orientation Event: June 1-2 Project Closure: Complete all follow-up activities by June 20 Duration: Approximately 18 weeks total, including closure activities. |
| Project Manager | Gloria Fisher (20 hours per week) |
| Approval Authority/Sponsor | Marcus Wilson, Head of HR (Project Sponsor, available 2 hours per week) |
| Assumptions or Constraints | Assumptions: - Approximately 12 new hires and 8 company participants will attend the quarterly orientations - Conference room will be available for the June 1st event - Stakeholders will provide required support for the program - Funding will be approved as needed for the project implementation Constraints: - June 1-2 orientation date is fixed and cannot change - Program must be fully developed within approximately 14 weeks. - Conference room reservations must be completed 15 days prior to use. - Project funding covers development and inaugural event only. |
| Proposed Solution(s) | Develop and conduct a structured two-day orientation consisting of: - Continental breakfast and networking session - A campus tour of the new hires - Benefits overview presentation - Catered lunch, "Unpack Your Perks" presentation. - Q&A session - Continuing education presentation - Technical onboarding support including equipment setup, badges, and supplies. |
| Project Priorities | 1. Schedule (Highest Priority): June 1st launch date must be met. 2. Quality: Orientation must effectively support new hires and improve retention. 3. Cost: the project costs of $14,000 should remain reasonable while ensuring program success. |
| Return on Investment (ROI) | Potential ROI is achieved through reduced employee turnover. Preventing the loss of only a few new hires can avoid multiple recruitment replacement costs at approximately $6,000 per employee. Additional benefits include higher employee engagement, productivity, and organizational commitment. |
| Risks (Potential) | - Stakeholder availability constraints - Delays in content development - Conference room reservation issues - Technology support failures - Catering service disruptions - Inability to complete development before June 1 - Insufficient executive participation - Lower than expected orientation effectiveness. |
| Resources Required | Personnel: Gloria Fisher (PM) Marcus Wilson (Sponsor) Hiroshi Tanaka (IT) Ursula Miller (Finance) Priya Sanders (Marketing) Sam Manning (Facilities) Marvin Coleman (Catering) Sunny Marsh (Benefits) Ram Finland (Continuing Education) Executive Leadership Team. Facilities & Equipment: Corporate conference room Audio Visual equipment for presentations Employee hardware i.e. laptops, phones etc. Stationery: badges, note pads, pens etc. Estimated Direct Project Costs: Breakfast: 20 paxs × $8 = $160 (Day 1), Day 2 - $8 x 12 = $96 Lunch: 20 pax × $12 = $240 Marketing materials: 12 × $50 = $600 Technical equipment: 12 × $1,200 = $14,400 Personnel Costs @ $50 per hour: - Project Manager 280hrs = $14,000 - Sponsor 28hrs = $1,400 - IT 20hrs = $1,000 - Finance 2hrs = $100 - Marketing 25hrs = $1,250 - HR Support 3hrs = $150 - IT Event Support = $200 Conference costs $500 per hr (Total hours = 10, day 1 8.5hrs and day 2 1.5hrs not charged to the project) = $5,000 Estimated Total Project Cost: $34,000 |