## Roadmap
Project Goal: Launch a new company website to increase online presence and improve customer engagement.
Milestone | Outcomes | Success Metric: | Timeframe | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Market Research and Planning | Understand user needs and define website requirements. | Completion of user surveys and market analysis report. | January - February | bar: Jan to Feb
2. Design Phase | Create a user-friendly and visually appealing website design. | Approval of wireframes and design mockups. | February - March | bar: Feb to Mar
3. Development Phase | Develop the website with all required features and functionalities. | Completion of website development and internal testing. | March-April | bar: Mar to Apr
4. Content Creation | Develop and integrate high-quality content for the website. | Approval of all website content. | March - April | bar: Mar to Apr
5. Testing and Quality Assurance | Ensure the website is bug-free and performs well. | Successful completion of beta testing with no critical issues. | April - May | bar: Apr to May
6. Launch and Marketing | Successfully launch the website and drive initial traffic. | Achieve 10,000 unique visitors in the first month. | May- June | bar: May to Jun

## Gantt chart
[7 empty] | J A N U A R Y | [30 empty] | F E B R U A R Y | [27 empty] | M A R C H | [30 empty] | A P R I L | [29 empty] | M A Y | [30 empty] | J U N E
Ref | Milestones/Tasks | Start Date | End Date | Duration (days) | Team | Dependencies | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1.1 | Planning |  |  |  |  | Milestone
| 1.1.1 Develop Project Charter and approval | 2026-02-16 | 2026-02-17 | 2 | bar: J A N U A R Y 2 to J A N U A R Y 14
| 1.1.2 Get Project Charter sign-off | 2026-02-18 | 2026-02-18 | 1 | bar: J A N U A R Y 2 to J A N U A R Y 14
| 1.1.3 Identify Stakeholders | 2026-02-19 | 2026-02-19 | 1 | bar: J A N U A R Y 2 to J A N U A R Y 14
| 1.1.4 Develop Stakeholder Register | 2026-02-20 | 2026-02-20 | 1 | bar: J A N U A R Y 2 to J A N U A R Y 14
| 1.1.5 Develop WBS | 2026-02-23 | 2026-02-23 | 1 | bar: J A N U A R Y 2 to J A N U A R Y 14
| 1.1.6 Develop Project Schedule | 2026-02-24 | 2026-02-24 | 1 | bar: J A N U A R Y 2 to J A N U A R Y 14
| 1.1.7 Develop budget and cost estimates | 2026-02-25 | 2026-02-25 | 1 | bar: J A N U A R Y 2 to J A N U A R Y 14
| 1.1.8 Develop Communications Plan | 2026-02-26 | 2026-02-26 | 1 | bar: J A N U A R Y 15 to J A N U A R Y 22
| 1.1.9 Reserve Conference Room | 2026-02-27 | 2026-02-27 | 1 | bar: J A N U A R Y 23 to J A N U A R Y 26
1.2 | Project Executing |  |  |  |  | Milestone
| 1.2.1 Orientation Program Design & Content Development | 2026-03-02 | 2026-03-27 | 20 | bar: J A N U A R Y 29 to F E B R U A R Y 11
| 1.2.2 Develop Orientation Materials & Welcome Packages | 2026-03-30 | 2026-04-24 | 20 | bar: J A N U A R Y 29 to F E B R U A R Y 11
| 1.2.3 Get approval on Welcome Packages and Content |  |  | 5 | bar: J A N U A R Y 29 to F E B R U A R Y 11
1.2.3 Logistics Coordination | bar: J A N U A R Y 29 to F E B R U A R Y 11
1.2.4 Source Employee Equipment | bar: J A N U A R Y 29 to F E B R U A R Y 11
1.2.4 Set-up Employee Equipment | bar: J A N U A R Y 29 to F E B R U A R Y 11
1.2.4 Confirm Packages and Content for Presentation | bar: J A N U A R Y 29 to F E B R U A R Y 11
| 1.2.5 Conduct Orientation Day 1 | 2001-06-01 | 2001-06-01 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.5.1. Breakfast | 2001-06-01 | 2001-06-01 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.5.2. Conduct Campus tour | 2001-06-01 | 2001-06-01 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.5.3. Present Innovations inc benefits | 2001-06-01 | 2001-06-01 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.5.4. Lunch | 2001-06-01 | 2001-06-01 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.5.5. Conduct Unpack Your Perks | 2001-06-01 | 2001-06-01 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.5.6. Conduct Q&A Sessions | 2001-06-01 | 2001-06-01 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.5.7. Presentation on continuing education opportunities | 2001-06-01 | 2001-06-01 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.6 Conduct Orientation Day 2: | 2001-06-02 | 2001-06-02 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.6.1.Breakfast | 2001-06-02 | 2001-06-02 | 1 | bar: F E B R U A R Y 12 to F E B R U A R Y 14
| 1.2.6.2.New Hires Receive Technical Support | 2001-06-02 | 2001-06-02 | 1 | bar: F E B R U A R Y 15 to F E B R U A R Y 18
| 1.2.6.3.New Hires Receive Corporate Badges and Supplies | 2001-06-02 | 2001-06-02 | 1 | bar: F E B R U A R Y 19 to M A R C H 4
1.3 | Project Closure |  |  |  |  | Milestone
| 1.3.1 Collect Feedback from New hires and existing employees | 2026-06-03 | 2026-06-05 | 3 | bar: M A R C H 9 to M A R C H 10
| 1.3.2 Evaluate Program Effectiveness | 2026-06-08 | 2026-06-10 | 3 | bar: M A R C H 9 to M A R C H 10
| 1.3.3 Financial Reconciliation & Cost Reporting | 2026-06-11 | 2026-06-12 | 2 | bar: M A R C H 9 to M A R C H 10
| 1.3.4. Run Lessons Learned workshop | 2026-06-15 | 2026-06-16 | 2 | bar: M A R C H 9 to M A R C H 10
| 1.3.5. Update Project Documentation | 2026-06-17 | 2026-06-17 | 1 | bar: M A R C H 9 to M A R C H 10
| 1.3.6 Transition Program to HR Operations | 2026-06-18 | 2026-06-18 | 1 | bar: M A R C H 9 to M A R C H 10
| 1.3.7 Project Closure Approval | 2026-06-19 | 2026-06-19 | 1 | bar: M A R C H 9 to M A R C H 10