## Scenario
Scenario: Office Renovation Project
Lydia is managing an office renovation project. A vendor has been hired to renovate an office space of approximately 16,000 square feet. Lydia employs 95 people. The company made arrangements for about 50 employees to work from home during this renovation. The vendor will need to partition off the workspace from the construction area to accommodate the 45 employees who will need to occupy the office during the renovation. The renovation will replace all worn carpets, paint the entire office space, replace old cube work areas, and create a combination of private work areas and open space work areas. About twenty additional electrical outlets will be included. The company is housed on the second and third floor of a large building in a busy office park. There are times when customers come to the office for assistance. At this time, there is only a small meeting room available for customer meetings. This accommodation will need to be planned. The CEO, Garcia Nandi, has set an aggressive schedule. She wants work to begin on or within the next 2 days, and complete the renovation within 60 days. Lydia feels this schedule will be difficult to meet but is committed to seeing the project through. Lydia has been assigned two core team members to help her with planning. One team member is new to the company. The other team member is an experienced facility manager with a track record of managing several successful renovations in the past. Budget is not a constraint. When asked about budget limits, the CEO replied, Whatever it takes.

## Risk Register Template
Project: Date:
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Customer support | Customer visit location | Injuries | HR | Threats | 1 | 5 | 5 | Reported injuries | Proper signage at the site
2 | Enviromental | Dust and fibres in the air | Employee health suffers | Enviromental | Threats | 4 | 4 | 16 | Emploee absenteeism due to health | Provide PPE - like masks
3 | Fast tracking | compressed milestones | Schedule slippage | PM | Threats | 4 | 5 | 20 | Milestones not met | Ensure proper resource planning
4 | New site | use of stairs | Injuries due to slipage | Enviromental | Threats | 2 | 4.5 | 9 | Reported injuries | Ensure the stairs are slip protected
5 | Permits - Electrical works | Delayed permits approval | Schedule delays | Electrical | Threats | 1 | 3 | 3 | Delayed permit | Plan for early permit requests
6 | Working from home - 50 Staff to work from home | Productivity reduces | missed dealines | HR | Threats | 2.5 | 3.5 | 8.75 | Missed deadlines | Train on working from home best practices
7 | Working on site - 45 Staff to work from site | Reduced productivity due to rennovation work | daily workload impacted | HR | Threats | 2.5 | 3.5 | 8.75 | Employee concerns | Plan for noisy work during less productive hrs
8 | Budget | No constraint | Adequate resources | Finance | Opportunity | 1 | 1 | 1 | None | Fund the request
9 | Project team assistant | Employee experienced in facility management | Quick issue resolution | PM | Opportunity | 3 | -3.5 | -10.5 | None | Incentivice the assistance
0
Total Risk Score
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low

## Example
Project: Off Site Date: June 19 20XX
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Management Support | 1. Great Event 2. Super Turnout | Increased motivation | Bill | O | 5 | -5 | -25 | High RSVP | 1. Market 2. Prizes
4 | Catering | Late Food Delivery | Delayed events | Food Services | T | 3.5 | 5 | 17.5 | None | Call 1-Day Prior
3 | Multiple Projects | Lack of capacity | Schedule delays | Bill | T | 4 | 4 | 16 | Missed deadlines | Use Staffing Mgt Plan
2 | Bad Weather | 1. Reduced Turnout 2. Late Start | Reduced impact | Jane | T | 3 | 4 | 12 | Weather Report | Ensure inside venue Plan B
Total Risk Score | [7 empty] | 20.5
May use the Project Risk Score: Total Negative scores - positive scores. Larger the gap--the more risk the project has.
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low