Scenario: May 1- Mile Highway Be Clean Project

ABC Company is a socially responsible organization and supports various social causes. Giving is a part of the organization culture and a key value. The CEO encourages all employees to be socially responsible. One of the social initiatives that ABC Company supports is Adopt-a-Highway. This initiative helps keep the Highways clear of trash and debris.

This month, about twenty employees aged 21 to 68, have signed up as volunteers for the Adopt-a-Highway project. Tamara is one of the volunteers and has been appointed as project manager for the project.

The objective of this project is to clean the trash and debris and place them in bags along a one mile stretch of Highway 11. Highway 11 connects two small cities and has heavy traffic at all times. The volunteers, along with the project manager, have code-named the project, May 1-Mile Highway Be Clean, chosen Saturday morning from 8:00 AM to 11:00 AM for this project. The team has planned the event, and Tamara has sent the agenda to all volunteers and other external stakeholders.

ABC will transport volunteers in a charter bus from their headquarters building at 7:30 AM to the highway site.

Each city will provide cleaning supplies like gloves, bags, and instructions on where to leave the filled bags of trash and debris. ABC Company is providing some cleaning supplies that are not available in the cities.

The bus will return to a designated pick-up location to transport volunteers back at 11:15 AM. Volunteers will be treated to a pizza lunch when they return to ABC Company.

The long-range weather forecast for the day of the event is only 20% rain. It is May. Normally, the average morning temperature is 75-80 degrees Fahrenheit (24-27 degree Celsius). Overall, the team is all set and hoping for the best.

| Strength (Cause) | Opportunity (Event) |
| --- | --- |
| Company is a socially responsible organization and this improves the corporate culture | The social responsibility may provide the opportunity for better publicity of the organisation |
| The CEO encourages all employees to be socially responsible | With CEO leading the social responsibility ensures by in from other employees thus more volunteers |
| About twenty employees aged 21 to 68 have signed up for the project | The diverse age set may provide a good setting for better working relationships |
| The organisation and employee desire to achieve the set objectives | The volunteers will be able to improved their social skills and responsibility |
| The work will be will be manual | This can be used as a way to keep fit |
| Weakness (Cause) | Weakness (Event) |
| Weather forecast for the day of the event is only 20% rain | If it rains there might be a delay or cancellation of the cleaning |
| The volunteers might be exposed to hazardous materials | This can lead to contamination of the volunteers |
| Traffic as the cleaning is been done in an inter linking road | This can lead to accidents to the volunteers |
| Catering as lunch is being provided | This can cause ordering mishap if the PM doesn’t take this into consideration |
| The organisation is offering transport | There can be delays in the volunteers arriving or being picked from the site |
| Health issues – the team comprises of volunteers aged between 21 - 68 | The older volunteers might be affected by health issues as the work is manual |